## Sheet1
Remaining efford
| Product backlog item | Sprint task | Volunteer | Status | Initial est. of efford | day1 (22/11) | day1 (23/11) | day1 (26/11) | day1 (27/11)
Sprint 1 |  |  |  |  | 36 | 22 | 5 | 0 | 0
| Use cases |  |  |  | 17 | 8 | 0 | 0 | 0
|  | UC1 | Filip | Done | 1 | 0
|  | UC2 | Filip | Done | 1 | 0 |  |  |  | Sprint 1 Burndown Chart
|  | UC3 | Morten | Done | 2 | 0
|  | UC4 | Bergar | Done | 3 | 0
|  | UC5 | Morten | Done | 3 | 3 | 0
|  | UC6 | Morten | Done | 1 | 0
|  | UC7 | Morten | Done | 1 | 0
|  | UC8 | Bergar | Done | 2 | 2 | 0
|  | UC9 | Bergar | Done | 3 | 3 | 0
| Use case model |  | Filip | Done | 2 | 1 | 0
| SSD |  | Bergar | Done | 2 | 0
| Operation contract |  | Bergar | Done | 3 | 2 | 0
| Interaction diagram |  |  |  | 4 | 4 | 0
|  | Communication Diagram | Morten | Done | 2 | 2 | 0
|  | Sequence Diagram | Filip | Done | 2 | 2 | 0
| Package Diagram |  | Bergar | Done | 2 | 2 | 0
| Class Diagram |  | Bergar | Done | 2 | 2 | 2 | 0
| C# Basic arctitecture |  | Morten | Done | 2 | 1 | 1 | 0
| System |  | Bergar | Done | 2 | 2 | 2 | 0
[6 empty] | day 1 (27/11) | day 2 (28/11) | day 3 (29/11)
Sprint 2 |  |  |  |  | 30 | 9 | 5 | 0
| Database |  |  |  | 15 | 0
|  | ER-Diagram | Morten | Done | 3 | 0
|  | User Table | Morten | Done | 3 | 0
|  | Document Table | Morten | Done | 3 | 0
|  | User-Document table | Morten | Done | 3 | 0
|  | Document-History table | Morten | Done | 3 | 0
System Architecture
|  | Implement GRASP |  |  | 9 | 6 | 3 | 0
|  | C/E/D Document | Bergar | Done | 3 | 1 | 0
|  | Database Connection | Morten | Done | 3 | 3 | 3 | 0
|  | GUI Client | Filip | Done | 3 | 2 | 0
Test
|  | test everything | All | Done | 6 | 3 | 2 | 0
[6 empty] | day 1 (4/12) | day 2 (6/12) | day 3 (7/12) | day 4 (10/12) | day 5 (11/12)
Sprint 3 |  |  |  |  | 110 | 98 | 82 | 65 | 55 | 35
| User directory |  |  |  | 5 | 2 | 0
|  | Personal root dir | Bergar | Done | 3 | 0
|  | shared root dir | Bergar | Done | 2 | 2 | 0
| User authentication |  |  |  | 6 | 3 | 0
|  | Username & Password relationship | Morten | Done | 2 | 0
|  | Storage of username & password | Morten | Done | 1 | 0
|  | Fetch and compare | Morten | Done | 3 | 3 | 0
| Sharing document |  |  |  | 10 | 6 | 0
|  | File input | Filip | Done | 3 | 1 | 0
|  | Server Code | Morten | Done | 3 | 1 | 0
|  | Share with permission | Morten | Done | 2 | 2 | 0
|  | Permission db (add field) | Morten | Done | 2 | 2 | 0
| Offline sync |  |  |  | 28 | 26 | 21 | 13 | 7 | 0
|  | Client to server connection | Filip | Done | 5 | 5 | 3 | 1 | 1 | 0
|  | Server to Client connection | Bergar | Done | 5 | 3 | 2 | 1 | 1 | 0
|  | Server handling new data (Simple) | Morten | Done | 4 | 4 | 2 | 0 | 0
|  | Client accepts all | Filip | Done | 3 | 3 | 3 | 3 | 2 | 0
|  | Server handling new data (Advanced) | Morten | Done | 4 | 4 | 4 | 3 | 0
|  | Server simple comparision of doc history | Morten | Done | 2 | 2 | 2 | 1 | 0
|  | Server merge of documents | Bergar & Morten | Done | 5 | 5 | 5 | 4 | 3 | 0
| Web client | Implement web client | Bergar | Done | 5 | 5 | 5 | 5 | 3 | 0
| ER-Diagram | ER-Diagram | Bergar | Done | 2 | 2 | 2 | 0
| File format | Documentation | Bergar | Done | 2 | 2 | 2 | 0
| Class diagram | Update class diagram | Bergar | Done | 2 | 2 | 2 | 2 | 0
Testing & Documenting
|  | Test Everything | All | NOT DONE | 30 | 30 | 30 | 30 | 30 | 25
|  | Document everything | All | NOT DONE | 20 | 20 | 20 | 15 | 15 | 10
Arteficial lines:

## Sheet2
| Actual Sprint | Ideal line
Initial | 36 | 36
Day 1 | 22 | 27 | [6 empty] | 0
Day 2 | 5 | 18
Day 3 | 0 | 9
Day 4 (END) | 0 | 0
|  |  |  | Actual Sprint | Ideal Line
|  |  | Initial | 30 | 30
|  |  | Day 1 | 9 | 20
|  |  | Day 2 | 5 | 10
|  |  | Day 3 (END) | 0 | 0
[7 empty] | Actual Sprint | Ideal Line
[6 empty] | Initial | 110 | 110
[6 empty] | Day 1 | 98 | 88
[6 empty] | Day 2 | 82 | 66
[6 empty] | Day 3 | 65 | 44
[6 empty] | Day 4 | 55 | 22
[6 empty] | Day 5 (END) | 35 | 0